## UAT Report
User Acceptance Test Report - aTendy Attendance App
Engineer | Lev Karavanov
Execution date | 22/04/2026
Environment | Local frontend http://localhost:5173, backend http://localhost:8081, PostgreSQL local demo DB; teacher and student accounts tested
Test cases for teachers and students
Name | 1. Sign in as teacher and student and verify role-based access
Design Date | 24/04/2026
Preconditions | Teacher and student accounts exist in the system
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Open the login page | Login form is shown | pass | Login page opened successfully.
2 | Enter teacher credentials and submit | Redirected to teacher dashboard | pass | Teacher account redirected to /teacher/dashboard.
3 | Log out | Returned to the login page | pass | Sign out returned to login page.
4 | Enter student credentials and submit | Redirected to student dashboard | pass | Student account redirected to /student/dashboard.
5 | As student, attempt to open a teacher-only page | Access is denied / redirected | pass | Student was redirected away from teacher route.
Post-condition | Each role can access only its own pages.
Test cases for teachers
Name | 2. Create a course and lecture as teacher
Design Date | 24/04/2026
Preconditions | Teacher is signed in
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Navigate to the Courses page | Course list is shown | pass | Courses page loaded successfully and displayed existing courses.
2 | Click 'Create course' and fill the form | Course form accepts input | pass | Course creation form accepted name and description.
3 | Submit the course form | Course is created and appears in the list | pass | Created course appeared in the course list.
4 | Click the icon 'Start lecture' | Lecture form is shown | pass | Create lecture dialog opened from course actions.
5 | Fill the lecture details and submit | Lecture dashboard is shown | pass | Fresh lecture was created and redirected to lecture dashboard.
Post-condition | Course and lecture exist in the system.
Test cases for students
Name | 3. Mark attendance as student using the lecture code
Design Date | 24/04/2026
Preconditions | Student is enrolled to the course and signed in
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Teacher has shared a valid active lecture code
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Click 'Enter code' | Lecture-code input is shown | pass | Mark Attendance dialog opened from student dashboard.
2 | Enter the lecture code | Code is accepted by the form | pass | Fresh active lecture code was accepted by the input field.
3 | Submit the form | 'Attendance marked' message is shown | pass | System displayed attendance marked confirmation and updated dashboard counters.
Post-condition | Attendance record is stored for the student.
Test cases for teachers and students
Name | 4. Open attendance-related pages and verify data is shown correctly
Design Date | 24/04/2026
Preconditions | At least one attendance record exists
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Student opens the attendance History | List of records is shown | pass | History page opened and displayed attendance-related information.
2 | Teacher opens Lectures page | All lectures are shown | pass | Lectures page showed existing lectures and join codes.
3 | Teacher clicks 'view dashboard' for a specific lecture | Present students list is shown | pass | Lecture dashboard displayed attendance statistics and present student list.
Post-condition | Attendance data is displayed for teacher and student flows.
Test cases for teachers
Name | 5. Create a course in English and verify that an English translation row is stored
Design Date | 24/04/2026
Preconditions | Teacher is signed in
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
UI locale is set to English
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Open the course creation form | Form is shown in English | pass | Course creation form opened in English.
2 | Enter the course name and description in English | Input is accepted | pass | English course name and description were accepted.
3 | Submit the form | Course is saved successfully | pass | Course was saved and appeared in the list.
4 | Query the course list / database | An English translation row exists for the course | pass | Course data was available in English after creation.
Post-condition | An English translation row is persisted for the new course.
Test cases for teachers
Name | 6. Add the same course in Russian and verify that the Russian version can be retrieved
Design Date | 24/04/2026
Preconditions | Course from test 5 exists with an English translation
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Open the course edit page | Edit form is shown | pass | Edit form opened for the created course.
2 | Switch the locale selector to Russian | Russian input fields are displayed | pass | UI switched to Russian labels.
3 | Enter the Russian name and description | Input is accepted | pass | Russian Cyrillic course name and description were accepted.
4 | Submit the form | Russian translation row is saved | pass | Russian text was saved.
5 | Request the course with locale = ru | Course data is returned in Russian | pass | Course list showed the Russian name and description when Russian locale was active.
Post-condition | Russian translation exists and is retrievable.
Test cases for teachers
Name | 7. Request course data with a missing locale and confirm fallback to the default locale
Design Date | 24/04/2026
Preconditions | A course exists with only one translation, for example English or Russian
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Request the course with an unavailable locale, for example fi | Server responds with course data | pass | Switching UI to Finnish still returned course data.
2 | Inspect the response language | Data is returned in the default or available locale | pass | Course data fell back to an available translation and did not fail.
Post-condition | Missing-locale requests fall back to available content.
Test cases for teachers
Name | 8. Save and retrieve Arabic or Cyrillic text and verify that UTF-8 works correctly
Design Date | 24/04/2026
Preconditions | Teacher is signed in
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Create or update a course with Arabic or Cyrillic name and description | Input is accepted without errors | pass | Cyrillic Russian course name and description were entered successfully.
2 | Submit the form | Course is stored successfully | pass | Course update completed successfully.
3 | Reopen the course or fetch it via API | Text is returned exactly as entered | pass | Cyrillic text was displayed correctly in the course list.
Post-condition | Non-Latin UTF-8 text is stored and retrieved without corruption.
Test cases for teachers
Name | 9. Teacher can upload a student list for the course
Design Date | 24/04/2026
Preconditions | Teacher is signed in
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
A course exists
A valid student-list XML file is prepared
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Open the course page | Course details are shown | pass | Course and enrollments page opened successfully.
2 | Click 'Enrollments' | List of enrolled students is shown | pass | Enrollments page displayed current roster.
3 | Click 'Upload enrollments' | File selector opens | pass | Upload enrollments control was available.
4 | Select the prepared student-list .xml file | File is selected and listed | pass | Prepared XML file was submitted to the upload endpoint.
5 | Confirm the upload | Success message is shown; students appear in the list | pass | Upload returned success and imported students appeared in enrollments.
Post-condition | All students from the XML file are added to the course.
Test cases for teachers
Name | 10. Teacher can add one student to the course
Design Date | 24/04/2026
Preconditions | Teacher is signed in
Executed by: | Lev Karavanov
Execution date: | 22/04/2026
A course exists
Step | Action | Expected System Response | Pass / Fail | Comment
1 | Open the course list | Courses list is shown | pass | Course list opened successfully.
2 | Click 'Enrollments' | List of enrolled students is shown | pass | Enrollments list opened for the selected course.
3 | Click 'Add student' | Add-student form is shown | pass | Add student dialog opened.
4 | Enter the student's credentials | Input is accepted and submitted | pass | Student first name, last name, and email were accepted.
5 | Look at the enrolled students list | The new student appears in the list | pass | Newly added student appeared in the enrollment table.
Post-condition | A single student is added to the course roster.
Summary
Passed steps | 40
Failed steps | 0
Blocked steps | 0
Overall result | Accepted in the local UAT environment. All 10 test cases passed after aligning the local database schema with the current application code.